## Sprint Backlog
YarnCraft Nepal — Sprint Backlog (Final / As-Built)
Flutter + Node/Express/MongoDB · 5 Sprints · 56 Tasks · ~190 Story Points · Prajesh Shrestha · 230477
Legend: Done = shipped as planned · Modified = built but changed · New = beyond original plan · Partial = simplified/dropped
Sprint | Task ID | Task / User Story | Screen | Priority | Story Points | Status | Notes
Sprint 1 — Authentication & Onboarding
| S1-01 | Splash / Welcome — brand tagline, Create Account and Sign In CTAs, Continue as Guest | Splash | High | 2 | Done | Loom background image added
| S1-02 | Sign In — email/phone, password show/hide, Remember Me, Forgot Password | Sign In | High | 3 | Modified | Remember Me shows 'Continue as <Name>' on next launch
| S1-03 | Forgot Password — send reset link, return to login | Forgot PW | High | 2 | Modified | Sends a real reset link via email (SMTP) + hosted reset page
| S1-04 | Sign Up — full name, email, phone (+977), password, terms | Sign Up | High | 5 | Modified | Phone exactly 10 digits; auto-login after signup
| S1-06 | Account Ready success screen — Go to Home / Complete Profile | Account Ready | High | 2 | Done
| S1-07 | Profile / Account — avatar, My Activity, settings, Log Out | Profile | High | 5 | Done | Admin users also see an Admin Panel entry
| S1-08 | Edit Profile — name, email, phone, DOB, gender | Edit Profile | High | 5 | Modified | Email now editable (uniqueness-checked) + profile photo upload; phone 10-digit
| S1-09 | Bottom navigation bar — Home, Search, Orders, Profile | Global | High | 3 | Done | Persists on authenticated screens
| S1-10 | Form validation system — errors, password strength, verified badges | All Forms | High | 3 | Done
Sprint 2 — Home Screen & Design System
| S2-01 | Design System — colour palette & Figma colour styles | Design System | High | 3 | Done
| S2-02 | Design System — typography scale & text styles | Design System | High | 2 | Done
| S2-03 | Design System — component library (all states) | Design System | High | 8 | Done | Largest task
| S2-04 | App top bar — logo, title, back, search, cart | Global | High | 2 | Done
| S2-05 | Home — Hero banner 'Discover Artisan Collections' + Explore CTA | Home | High | 3 | Modified | Real background image behind Featured Artisan Collection
| S2-06 | Home — Quick filter chip row | Home | High | 2 | Done
| S2-07 | Home — Trending Textures horizontal scroll row | Home | High | 3 | Done | Live products from backend
| S2-08 | Home — Meet the Artisans section + Fair Trade badge | Home | High | 3 | Modified | 'Legacy of Dhaka' section with background image
| S2-09 | Home — Shop by Origin 2x2 regional grid | Home | High | 3 | Partial | Category chips used instead of the regional grid
Sprint 3 — Browse, Filter & Product Detail
| S3-01 | Listing — search bar, result count, Load More | Listing | High | 3 | Partial | Search + count done; single load (no pagination)
| S3-02 | Listing — cards with thumbnail, name, price, Artisan Verified badge | Listing | High | 5 | Done | Responsive grid (adapts to device width)
| S3-03 | Listing — New Arrivals / Best Seller / Popular chips | Listing | Med | 2 | Done
| S3-04 | Filter & Sort — Material chips with active state | Filter | High | 5 | Done | Bottom sheet
| S3-05 | Filter & Sort — Origin, Colour swatches, Usage, Apply | Filter | High | 5 | Done
| S3-06 | Product Detail — hero image, share/wishlist, provenance tag | Product Detail | High | 5 | Done
| S3-07 | Product Detail — price/metre, colour swatches, qty stepper, Add to Cart | Product Detail | High | 5 | Modified | Colours now admin-defined (any number); quantity typeable; sold per metre
| S3-08 | Product Detail — Detailed Breakdown accordion | Product Detail | High | 3 | Modified | Added Availability (meters), Batch No., Verified Supplier rows
| S3-09 | Product Detail — Ratings & Reviews | Product Detail | High | 5 | Modified | Reviews only allowed after ordering; submitted reviews render here
| S3-10 | Product Detail — Related Products row | Product Detail | Med | 3 | Done
Sprint 4 — Cart, Checkout & Order Confirmation
| S4-01 | Cart — item rows, qty stepper, remove | Cart | High | 5 | Modified | Rows show colour swatch + Made in Nepal/India & Verified Supplier badges
| S4-02 | Cart — Order Summary + Proceed to Payment | Cart | High | 3 | Modified | Added Bulk Discount (10% for orders >= 100 m) line
| S4-03 | Checkout — artisan trust notice banner | Checkout | High | 2 | Done
| S4-04 | Checkout — Delivery Information form | Checkout | High | 5 | Done
| S4-05 | Checkout — Payment Method | Checkout | High | 5 | Modified | Cash on Delivery + Pay Online with eSewa (demo); WhatsApp option dropped
| S4-06 | Checkout — Order Summary + Confirm | Checkout | High | 3 | Modified | Delivery fee NPR 150 (not platform fee 250); totals reflect bulk discount
| S4-07 | Checkout — Estimated Delivery display | Checkout | High | 2 | Done
| S4-08 | Product Detail — sticky Add to Cart + WhatsApp inquiry | Product Detail | High | 3 | Partial | Sticky Add to Cart done; WhatsApp inquiry not implemented
| S4-09 | Order Confirmation — 'Order Request Received!' screen | Confirmation | High | 3 | Done
| S4-10 | Cart persists across restart (backend sync) | Cart | High | 3 | New | GET/PUT cart, restored on launch
| S4-11 | Product images in checkout order summary | Checkout | Med | 1 | New
Sprint 5 — Saved, About, Contact, Orders & Admin
| S5-01 | Saved / Favorites — 2-column grid + Add to Cart | Saved | High | 5 | Done | Responsive grid
| S5-02 | Save / unsave toggle — filled vs outline heart | Global | High | 3 | Done
| S5-03 | About — 'Bridging the Gap' hero + Get Directions | About | Med | 3 | Done | Himalayan background image
| S5-04 | About — Our Heritage text + stats grid | About | Med | 3 | Done
| S5-05 | About — value icon cards (Fair Trade, Natural, Community) | About | Med | 2 | Done
| S5-06 | About — Faces of YarnCraft artisan profile cards | About | Med | 3 | Done | Maya Gurung & Rajesh Shrestha with photos
| S5-07 | Contact — phone/email + Send Message WhatsApp CTA | Contact | Med | 3 | Done
| S5-08 | Contact — Inquiry form + FAQ accordion | Contact | Med | 3 | Done
| S5-09 | Order History — status badge, Reorder, View Details | Account | Med | 5 | Modified | Added Mark as Received + Write a Review after delivery; Reorder not built
| S5-10 | Admin — product dashboard (list, edit, delete) | Admin | High | 5 | New | RBAC-protected
| S5-11 | Admin — create/edit product form (name, price, category, image) | Admin | High | 5 | New
| S5-12 | Admin — set Available Meters (stock) & Colors per product | Admin | High | 3 | New
| S5-13 | Admin — role-based access (admin-only panel) | Global | High | 2 | New
| S5-14 | Responsive layout — adaptive grids + text-scale clamp | Global | Med | 3 | New | Fits any device size
| S5-15 | App imagery — splash & section background images | Global | Low | 2 | New | Loom, artisans, Dhaka
|  | TOTAL |  |  | 185 | 54 tasks